## Tasks
Task Name | Bucket Name | Progress | Priority | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed Checklist Items
Quality Assurance Checks | Post Implementation Phase | Not started | Medium | 09/25/2025 |  |  | false | false
Daily Installations | Deployment Phase | Not started | Medium | 09/25/2025 | 11/24/2025 | 12/31/2026 | true | false
Customers Responsibility Mapping | Setup and Mobilization | In progress | Medium | 09/25/2025 | 11/03/2025 | 11/20/2025 | false | false |  | 2/7
Get PO from each contractor | Setup and Mobilization | Completed | Medium | 10/01/2025 |  |  | false | false | 10/02/2025
Summarize project results and lessons learned | Closing | Not started | Medium | 09/25/2025 |  |  | false | false
Handover documentation | Post Implementation Phase | Not started | Medium | 09/25/2025 |  |  | false | false
Procurement and Configuration | Setup and Mobilization | In progress | Medium | 10/01/2025 | 09/10/2025 | 11/07/2025 | false | false |  | 4/7
Procurement | Planning Phase | Completed | Medium | 09/25/2025 | 10/01/2025 | 10/15/2025 | false | false | 10/02/2025 | 1/1
Pre-deployment Validation | Setup and Mobilization | Not started | Important | 09/25/2025 | 10/01/2025 | 10/31/2025 | false | false |  | 3/7
HSE Setup | Planning Phase | Not started | Medium | 09/25/2025 | 10/01/2025 | 12/31/2025 | false | false |  | 0/2
Resource Management | Setup and Mobilization | Not started | Medium | 09/25/2025 | 10/27/2025 | 10/27/2025 | false | false |  | 0/2
Customer Data Linking | Deployment Phase | Not started | Medium | 09/25/2025 | 11/24/2025 | 02/20/2026 | false | false
Post-Implementation support | Post Implementation Phase | Not started | Medium | 09/25/2025 |  |  | false | false
Installer Team Deployment | Deployment Phase | In progress | Medium | 09/25/2025 | 11/10/2025 | 11/21/2025 | false | false |  | 2/3
Conduct team performance reviews | Post Implementation Phase | Not started | Medium | 09/25/2025 |  | 09/08/2026 | true | false
Testing | Deployment Phase | Not started | Medium | 09/25/2025 | 02/21/2025 | 02/20/2026 | false | false
Project Dashboard | Setup and Mobilization | In progress | Important | 09/25/2025 | 09/10/2025 | 10/24/2025 | false | false |  | 0/2
Operational Planning | Setup and Mobilization | In progress | Important | 09/25/2025 | 11/03/2025 | 12/01/2025 | false | false |  | 1/7
Customer Engagement | Deployment Phase | Not started | Important | 09/25/2025 | 11/25/2025 | 04/24/2026 | false | false |  | 0/4
Assembly Preparation | Planning Phase | In progress | Medium | 09/25/2025 | 10/15/2025 | 10/31/2025 | false | false |  | 1/2
Project Governance | Setup and Mobilization | Not started | Medium | 09/25/2025 | 10/01/2025 | 10/20/2025 | false | false
Data Integration | Planning Phase | Not started | Medium | 09/25/2025 | 10/01/2025 | 12/05/2025 | false | false |  | 0/3
Communications and rollout strategy | Setup and Mobilization | In progress | Important | 09/25/2025 | 09/01/2025 | 10/31/2025 | false | false |  | 12/20
Technology Architecture and system mapping integration | Setup and Mobilization | In progress | Medium | 09/25/2025 | 09/29/2025 | 12/05/2025 | false | false |  | 1/6
Product training | Deployment Phase | Completed | Medium | 09/25/2025 |  |  | false | false | 10/13/2025 | 0/1
Operational Readiness | Planning Phase | Not started | Important | 09/25/2025 | 10/01/2025 | 11/28/2025 | false | false |  | 0/3
Commissioning | Deployment Phase | Not started | Medium | 09/25/2025 | 11/24/2025 | 04/17/2026 | false | false
Report Weekly status | Deployment Phase | Not started | Medium | 09/25/2025 | 11/24/2025 | 12/31/2027 | true | false

## Date of Data
date
2025-10-22