## Sheet15
WS7761 Projects Tasks
Closing
Not started
Medium
Summarize project results and lessons learned
Deployment Phase
In progress
Medium
Installer Team Deployment
Not started
High
Customer Engagement
Medium
Commissioning
Customer Data Linking
Daily Installations
Product training
Report Weekly status
Testing
Planning Phase
Completed
Medium
Procurement
In progress
Medium
Assembly Preparation
Not started
Medium
Data Integration
HSE Setup
Operational Readiness
Post Implementation Phase
Not started
Medium
Conduct team performance reviews
Handover documentation
Post-Implementation support
Quality Assurance Checks
Test Task
Setup and Mobilization
Completed
Medium
Get PO from each contractor
In progress
Medium
Communications and rollout strategy
Customers Responsibility Mapping
Operational Planning
Procurement and Configuration
Project Dashboard
Technology Architecture and system mapping integration
Not started
Medium
Pre-deployment Validation
Project Governance
Resource Management
Grand Total

## Tasks
Task Name | Bucket Name | Progress | Priority | Start date | Due date | Completed Date | Completed Checklist Items
Quality Assurance Checks | Post Implementation Phase | Not started | Medium
Daily Installations | Deployment Phase | Not started | Medium | 11/24/2025 | 12/31/2026
Customers Responsibility Mapping | Setup and Mobilization | In progress | Medium | 11/03/2025 | 11/20/2025 |  | 2/7
Get PO from each contractor | Setup and Mobilization | Completed | Medium |  |  | 10/02/2025
Summarize project results and lessons learned | Closing | Not started | Medium
Handover documentation | Post Implementation Phase | Not started | Medium
Procurement and Configuration | Setup and Mobilization | In progress | Medium | 09/10/2025 | 10/10/2025 |  | 4/7
Procurement | Planning Phase | Completed | Medium | 10/01/2025 | 10/15/2025 | 10/02/2025 | 1/1
Pre-deployment Validation | Setup and Mobilization | Not started | Medium | 10/01/2025 | 10/22/2025 |  | 2/7
HSE Setup | Planning Phase | Not started | Medium | 10/01/2025 | 12/31/2025
Resource Management | Setup and Mobilization | Not started | Medium | 10/27/2025 | 10/27/2025 |  | 0/2
Customer Data Linking | Deployment Phase | Not started | Medium | 11/24/2025 | 02/20/2026
Post-Implementation support | Post Implementation Phase | Not started | Medium
Installer Team Deployment | Deployment Phase | In progress | Medium | 11/10/2025 | 11/21/2025 |  | 2/3
Conduct team performance reviews | Post Implementation Phase | Not started | Medium |  | 09/08/2026
Testing | Deployment Phase | Not started | Medium | 02/21/2025 | 02/20/2026
Project Dashboard | Setup and Mobilization | In progress | Medium | 09/10/2025 | 10/01/2025
Operational Planning | Setup and Mobilization | In progress | Medium | 11/03/2025 | 12/01/2025 |  | 1/7
Customer Engagement | Deployment Phase | Not started | High | 11/25/2025 | 04/24/2026 |  | 0/4
Assembly Preparation | Planning Phase | In progress | Medium | 10/15/2025 | 12/09/2025 |  | 1/2
Project Governance | Setup and Mobilization | Not started | Medium | 10/01/2025 | 10/20/2025
Data Integration | Planning Phase | Not started | Medium | 10/01/2025 | 12/05/2025 |  | 0/3
Communications and rollout strategy | Setup and Mobilization | In progress | Medium | 09/01/2025 | 10/31/2025 |  | 11/20
Technology Architecture and system mapping integration | Setup and Mobilization | In progress | Medium | 09/01/2025 | 09/30/2025 |  | 1/6
Product training | Deployment Phase | Not started | Medium |  |  |  | 0/1
Operational Readiness | Planning Phase | Not started | Medium | 10/01/2025 | 10/10/2025 |  | 0/2
Commissioning | Deployment Phase | Not started | Medium | 11/24/2025 | 04/17/2026
Report Weekly status | Deployment Phase | Not started | Medium | 11/24/2025 | 12/31/2027
Test Task | Post Implementation Phase | Not started | Medium

## Progress
Progress | Count of Task Name
Not started | 19
In progress | 8
Completed | 2
Grand Total | 29

## Priority
Priority | Count of Task Name
Medium | 28
High | 1
Grand Total | 29

## Bucket
Bucket Name | Count of Bucket Name
Setup and Mobilization | 10
Deployment Phase | 8
Post Implementation Phase | 5
Planning Phase | 5
Closing | 1
Grand Total | 29

## Dashboard
WS7761 Projects Tasks
Closing
Not started
Medium
Summarize project results and lessons learned
Deployment Phase
In progress
Medium
Installer Team Deployment
Not started
High
Customer Engagement
Medium
Commissioning
Customer Data Linking
Daily Installations
Product training
Report Weekly status
Testing
Planning Phase
Completed
Medium
Procurement
In progress
Medium
Assembly Preparation
Not started
Medium
Data Integration
HSE Setup
Operational Readiness
Post Implementation Phase
Not started
Medium
Conduct team performance reviews
Handover documentation
Post-Implementation support
Quality Assurance Checks
Test Task
Setup and Mobilization
Completed
Medium
Get PO from each contractor
In progress
Medium
Communications and rollout strategy
Customers Responsibility Mapping
Operational Planning
Procurement and Configuration
Project Dashboard
Technology Architecture and system mapping integration
Not started
Medium
Pre-deployment Validation
Project Governance
Resource Management

## Sheet13
IMPORTANT DETAIL
In order to insert a suggestion that uses a PivotTable or formula, your data was organized in columns with a single header row.
| Field1 | Field2 | Field3 | Field4
| Daily Installations | Deployment Phase | Not started | Medium
| Customers Responsibility Mapping | Setup and Mobilization | In progress | Medium
| Get PO from each contractor | Setup and Mobilization | Completed | Medium
| Summarize project results and lessons learned | Closing | Not started | Medium
| Handover documentation | Post Implementation Phase | Not started | Medium
| Procurement and Configuration | Setup and Mobilization | In progress | Medium
| Procurement | Planning Phase | Completed | Medium
| Pre-deployment Validation | Setup and Mobilization | Not started | Medium
| HSE Setup | Planning Phase | Not started | Medium
| Resource Management | Setup and Mobilization | Not started | Medium
| Customer Data Linking | Deployment Phase | Not started | Medium
| Post-Implementation support | Post Implementation Phase | Not started | Medium
| Installer Team Deployment | Deployment Phase | In progress | Medium
| Conduct team performance reviews | Post Implementation Phase | Not started | Medium
| Testing | Deployment Phase | Not started | Medium
| Project Dashboard | Setup and Mobilization | In progress | Medium
| Operational Planning | Setup and Mobilization | In progress | Medium
| Customer Engagement | Deployment Phase | Not started | High
| Assembly Preparation | Planning Phase | In progress | Medium
| Project Governance | Setup and Mobilization | Not started | Medium
| Data Integration | Planning Phase | Not started | Medium
| Communications and rollout strategy | Setup and Mobilization | In progress | Medium
| Technology Architecture and system mapping integration | Setup and Mobilization | In progress | Medium
| Product training | Deployment Phase | Not started | Medium
| Operational Readiness | Planning Phase | Not started | Medium
| Commissioning | Deployment Phase | Not started | Medium
| Report Weekly status | Deployment Phase | Not started | Medium